## Sheet1
Task | Start Date | Duration | End Date
Project Start | 2019-02-01 | 1 | 2019-02-02 | NOTE: | To change Date-Range for X-Axis. Double click to format the chart area.
Project Initial Design | 2019-02-01 | 109 | 2019-05-21 |  | In the drop-down, select 'Horizontal (Value) Axis', then the 'Axis Options' tab, then the 'Axis Options' menu.
Develop Project Ideas | 2019-02-01 | 94 | 2019-05-06 |  | Input desired dates for the Minimum and Maximum Bounds. They will change to numerical values.
Chose a Design | 2019-05-06 | 7 | 2019-05-13
Develop Design with Research | 2019-05-13 | 8 | 2019-05-21 |  | You can add/remove sections by simply inserting/deleting Excel rows in the table to the left.
Design Rover | 2019-05-21 | 244 | 2020-01-20 |  | Colors need to be changed by hand, that's less necessary but it looks nicer!
Create Block Diagram | 2019-05-21 | 20 | 2019-06-10
Create/Update Comprehensive CAD | 2019-05-27 | 238 | 2020-01-20
Find All Parts/Vendors | 2019-06-01 | 214 | 2020-01-01
Itemize Electric Specs for Battery | 2019-07-01 | 184 | 2020-01-01 |  |  | Project Start/End
Create Circuit Board | 2020-01-01 | 6 | 2020-01-07 |  |  | Main Task
Order/Print Parts | 2020-01-01 | 19 | 2020-01-20 |  |  | Subtask
Design Software | 2019-07-01 | 184 | 2020-01-01 |  |  | Data Compliation
Write UI | 2019-07-01 | 62 | 2019-09-01 |  |  | Wiggle Room
Communication | 2019-09-01 | 122 | 2020-01-01 |  |  | Project Review
Design Arm | 2019-12-01 | 62 | 2020-02-01
Create Comprehensive CAD | 2019-12-01 | 47 | 2020-01-17
Find All Parts/Vendors | 2020-01-10 | 20 | 2020-01-30
Itemize Electric Specs for Battery | 2020-01-20 | 12 | 2020-02-01
Create Circuit Board Layout | 2020-01-20 | 12 | 2020-02-01
Order/Print Parts | 2020-01-20 | 12 | 2020-02-01
Proof of Concept Testing | 2020-01-01 | 31 | 2020-02-01
Rover Movement - Stage 1 | 2020-01-01 | 19 | 2020-01-20
Arm Movement - Stage 1 | 2020-01-20 | 12 | 2020-02-01
Sensors | 2020-01-01 | 14 | 2020-01-15
Build Rover | 2020-01-20 | 39 | 2020-02-28
Assemble Mechanical Components | 2020-01-20 | 39 | 2020-02-28
Assemble Electrical Components | 2020-01-20 | 39 | 2020-02-28
Build Arm | 2020-02-01 | 36 | 2020-03-08
Assemble Mechanical Components | 2020-02-01 | 36 | 2020-03-08
Assemble Electrical Components | 2020-02-01 | 36 | 2020-03-08
Integrate Software/Test | 2020-02-28 | 30 | 2020-03-29
Rover Movement - Stage 2 | 2020-02-28 | 30 | 2020-03-29
Arm Movement - Stage 2 | 2020-02-28 | 30 | 2020-03-29
Compilation of Data | 2020-03-29 | 11 | 2020-04-09
Planned Wiggle Room | 2020-04-09 | 7 | 2020-04-16
Project End | 2020-04-16 | 1 | 2020-04-17
Review | 2020-04-17 | 2 | 2020-04-19
2017-01-04